## Blueprint Pengerjaan Frontend W
Tahap | Modul / Kategori | Task Pengerjaan (Detail) | Integrasi API Backend | Fitur Enterprise (Yang Masuk) | Estimasi Status
SPRINT 1 | Setup & Pondasi | Inisialisasi Next.js 14, TailwindCSS, dan Shadcn UI. | - | - | ⬜ To Do
SPRINT 1 | Setup & Pondasi | Konfigurasi Zustand (State) & TanStack Query (Data Fetching). | - | - | ⬜ To Do
SPRINT 1 | Setup & Pondasi | Setup Toast Notifications (Notifikasi Sukses/Gagal). | - | - | ⬜ To Do
SPRINT 2 | Auth & Onboarding | Buat UI Landing Page (opsional/halaman jualan). | - | - | ⬜ To Do
SPRINT 2 | Auth & Onboarding | Buat halaman Login & Register (/auth/login). | API NextAuth / JWT | 🔐 Alur Auth | ⬜ To Do
SPRINT 2 | Auth & Onboarding | Buat halaman Onboarding Tenant (Setup nama gudang pertama). | POST /api/warehouses | 🔐 Gateway SaaS | ⬜ To Do
SPRINT 3 | Global Layout | Buat Sidebar Navigation yang bisa di-collapse. | - | 📱 Responsivitas | ⬜ To Do
SPRINT 3 | Global Layout | Buat Top Navbar (Search, Tenant Badge, Profile). | - | - | ⬜ To Do
SPRINT 3 | Global Layout | Setup Skeleton Loading global & halaman Error 404/500. | - | ⏳ Skeleton Loading | ⬜ To Do
SPRINT 4 | Master Data UI | UI Tabel Produk dengan Server-side Pagination & Filter. | GET/POST /api/products | 🔍 Pagination & Filter | ⬜ To Do
SPRINT 4 | Master Data UI | UI Form Tambah Produk (Support Barcode Scanner Input). | POST /api/products | 📱 Mode Scanner | ⬜ To Do
SPRINT 4 | Master Data UI | UI Manajemen Gudang & Ilustrasi Empty State. | GET /api/warehouses | ⏳ Empty States | ⬜ To Do
SPRINT 4 | Master Data UI | UI Generate Lokasi Rak/Bin secara massal. | GET/POST /api/locations | - | ⬜ To Do
SPRINT 4 | Master Data UI | Desain Printable untuk Label Barcode Rak/Produk. | - | 🖨️ Printable Layouts | ⬜ To Do
SPRINT 5 | Inbound UI | UI Form Receiving (Penerimaan dari Supplier). | POST /api/v1/receiving | - | ⬜ To Do
SPRINT 5 | Inbound UI | UI Put-away (Tampilan khusus Tablet/PDA untuk Operator). | POST /api/v1/put-away | 📱 Mode Tablet | ⬜ To Do
SPRINT 6 | Inventory UI | UI Tabel Stok Real-time (Advanced Filter per Rak/Zone). | GET /api/v1/storage/stock | 🔍 Advanced Filtering | ⬜ To Do
SPRINT 6 | Inventory UI | UI Stock Opname (Form input aktual fisik vs sistem). | POST /api/v1/storage/opname | - | ⬜ To Do
SPRINT 6 | Inventory UI | Desain Printable Worksheet (Kertas Kerja Stock Opname). | - | 🖨️ Printable Layouts | ⬜ To Do
SPRINT 7 | Outbound UI | UI Cek Order (Validasi ketersediaan barang). | GET /api/v1/order/check | - | ⬜ To Do
SPRINT 7 | Outbound UI | UI Smart Picking (Rute operator ambil barang FIFO/FEFO). | POST /api/v1/order/pick | 📱 Mode Tablet | ⬜ To Do
SPRINT 7 | Outbound UI | UI Catat Shipment & Generate Nomor DO Otomatis. | API shipment & generate | - | ⬜ To Do
SPRINT 7 | Outbound UI | Desain Printable Surat Jalan / Delivery Order (DO). | - | 🖨️ Printable Layouts | ⬜ To Do
SPRINT 8 | Dashboard UI | UI Widget Statistik & Grafik Fast/Slow Moving Items. | GET /api/dashboard/analytics | - | ⬜ To Do
SPRINT 9 | Finishing | Testing Responsivitas di layar HP, Tablet, dan Desktop. | - | 📱 Responsivitas | ⬜ To Do
SPRINT 9 | Finishing | Pembatasan hak akses (Role-based UI) antara Admin & Operator. | - | 🔐 Akses Keamanan | ⬜ To Do